## Sheet1
Test Module / Feature: Suppliers Page
Tester: | [6 empty] | Pass | Fail | NOT RUN | Blocked | Total
Date: 4/5/2015 | [6 empty] | 79.55% | 0% | 0% | 0% | 79.55%
Test Precondition: 01 TC - Log In and Index Page
3 | Suppliers - User Interface
TCID | Test Scenario | Expected Result | Sample Data | Observed Output | Pass / Fail | Remarks
UITC_S01 | Suppliers Page Label | Suppliers Page label should be present and "Suppliers Page" should be heard |  |  | PASS
UITC_S02 | Add Supplier Button | Button label: Add Supplier Button color: Green Should be able to hear: Alt + A Add Supplier |  |  | PASS |  | Notes: User Interface Testing - Most test scenarios require you to hear a text or a label. For table reading / hearing: use arrow keys For form input and buttons: use tab keys Issue Log: https://github.com/joegeneq/apc-softdev-it111-06/issues * Optional Scenarios are not included in the testing
UITC_S03 | Manage Suppliers Button | Button label: Manage Supplier Button color: Red Should be able to hear: Manage Suppliers Alt + M |  |  | PASS
UITC_S04 | Suppliers table | A table used for viewing should be present It should have the following columns and these should be heard: Supplier Name Contact No Contact Person City Email |  |  | PASS |  | OVERALL REMARKS: The team passed all the test cases but with a lot of rushed changes before the deadline. The QA team had a hard time testing the system because of the abrupt changes made by the developers. Next time please finalize your testing documents before the QA team starts testing to avoid repetitive task and to not disrupt the schedule.
UITC_S05 | Back to Home button | Button Label: Back to Home Button color: Blue Should be able to hear: Alt + H Back to Home |  |  | PASS
4.1 | Suppliers - Functionality
FTC_S01 | Click Add Supplier button or Press Alt + A | Should be redirected to the Create Supplier form |  |  | PASS
FTC_S02 | Click Manage Suppliers button or Press Alt + M | Should be redirected to Manage Suppliers page |  |  | PASS
FTC_S03 | Click Back to Home button or Press Alt + H | Should be redirected to Index Page |  |  | PASS
3.2 | Add Supplier - User Interface
UITC_SA01 | Add Supplier Label | Add Supplier Label should be present and "Add Supplier" should be heard |  |  | PASS
UITC_SA02 | Supplier Name textbox field | Textbox field labeled Supplier name should be present Should be able to hear: Supplier Name Edit |  |  | PASS
UITC_SA03 | Contact Number textbox field | Textbox field labeled Contact Number should be present Should be able to hear: Contact number Edit |  |  | PASS
UITC_SA04 | Contact Person textbox field | Textbox field labeled Contact Person should be present Should be able to hear: Contact Person Edit |  |  | PASS
UITC_SA05 | Address label | Address label should be present and "Address" should be heard |  |  | PASS
UITC_SA06 | House Number textbox field | Textbox field labeled House Number should be present Should be able to hear: House Number Edit |  |  | PASS
UITC_SA07 | Street textbox field | Textbox field labeled Street should be present Should be able to hear: Street Edit |  |  | PASS
UITC_SA08 | City textbox field | Textbox field labeled City should be present Should be able to hear: City Edit |  |  | PASS
UITC_SA09 | Zip Code textbox field | Textbox field labeled Zip Code should be present Should be able to hear: Zip Code Edit |  |  | PASS
UITC_SA10 | Country dropdown list | Dropdown box labeled Country and its data should be present Should be able to hear: Country Combo box collapse: Country data |  |  | PASS
UITC_SA11 | Email textbox field | Textbox field labeled Email should be present Should be able to hear: Email Edit |  |  | PASS
UITC_SA12 | Create Button | Button label: Create Button color: Green Should be able to hear: Create |  |  | PASS
UITC_SA13 | Back to Suppliers button | Button label: Back to Suppliers Button color: Blue Should be able to hear: Back to Suppliers Page Alt + B |  |  | PASS
3.3 | Add Supplier - Functionality
FTC_SA01 | Input Supplier Name | Input for Supplier name should appear in the textbox field Should be able to hear per letter / character typed |  |  | PASS
FTC_SA02 | Input Contact Number | Input for Contact number should appear in the textbox field Should be able to hear per number / character typed |  |  | PASS | should only accept numeric values
FTC_SA03 | Input Contact Person | Input for Customer name should appear in the textbox field Should be able to hear per letter / character typed |  |  | PASS
FTC_SA04 | Input House Number | Input for House Number should appear in the textbox field Should be able to hear per letter / character typed |  |  | PASS
FTC_SA05 | Input Street | Input for Street should appear in the textbox field Should be able to hear per letter / character typed |  |  | PASS
FTC_SA06 | Input City | Input for City should appear in the textbox field Should be able to hear per letter / character typed |  |  | PASS
FTC_SA07 | Input Zip Code | Input for Zip Code should appear in the textbox field Should be able to hear per number typed |  |  | PASS | The zip code field should only accept alphanumeric values; Symbols or special characters should not be accepted. The code should be limited to 5 digits only.
FTC_SA08 | Choose Country | Chosen Country should appear and be heard |  |  | PASS | Please create a maintenance module (CRUD) for the country list; Do not display static values in the dropwdown field for system maintenance and contingency.
FTC_SA09 | Input Email | Input for Email should appear in the textbox field Should be able to hear per letter / character typed |  |  | PASS | Please improve email validation
FTC_SA10 | Click Create Button | Supplier should be created and viewed at the Suppliers page |  |  | PASS
FTC_SA11 | Click Back to Home Button or Press Alt + B | Should be redirected back to Home Page |  |  | PASS
3.3.1 | Add Supplier - Functionality (Negative Testing)
FTC_SAN01 | Supplier Name: Leave Blank | Validation message should appear: Supplier Name cannot be blank |  | PASSED | NOT RUN | Improve on notifying the users about incomplete fields | There's something wrong with the dropdown list of the Pass/Fail column under 3.3.1 . The verdict for this section is stated in the Observed Output column. Thank you!
FTC_SAN02 | Contact Person: Leave Blank | Validation message should appear: Contact Person cannot be blank |  | PASSED | NOT RUN | Improve on notifying the users about incomplete fields
FTC_SAN03 | Contact Number: Leave Blank | Validation message should appear: Contact Number cannot be blank |  | PASSED | NOT RUN | Improve on notifying the users about incomplete fields
FTC_SAN04 | House Number: Leave Blank | Validation message should appear: House Number cannot be blank |  | PASSED | NOT RUN | Improve on notifying the users about incomplete fields
FTC_SAN05 | Street: Leave Blank | Validation message should appear: Street cannot be blank |  | PASSED | NOT RUN | Improve on notifying the users about incomplete fields
FTC_SAN06 | City: Leave Blank | Validation message should appear: City cannot be blank |  | PASSED | NOT RUN | Improve on notifying the users about incomplete fields
FTC_SAN07 | Email: Leave Blank | Validation message should appear: Email cannot be blank |  | PASSED | NOT RUN | Improve on notifying the users about incomplete fields
FTC_SAN08 | Click Create Button | Supplier should not be created |  | PASSED | NOT RUN | Improve on notifying the users about incomplete fields
FTC_SAN09 | Click Back to Suppliers Page or Press Alt + B | Should be redirected back to Suppliers Page |  | PASSED | NOT RUN | Improve on notifying the users about incomplete fields
3.4 | Manage Supplier - User Interface
UITC_SM01 | Manage Suppliers Label | Manage Suppliers Label should be present and "Manage Suppliers" should be heard |  |  | PASS
UITC_SM03 | Search box | Search boxes should be present after each respective column name |  |  | PASS
UITC_SM04 | Added data from "Add Supplier" | Data added from "Add Supplier - Functionality" test scenario should be present in the table |  |  | PASS
UITC_SM05 | View button | An eye icon should be present under the unnamed column on the right |  |  | PASS
UITC_SM06 | Edit button | An pencil icon should be present under the unnamed column on the right |  |  | PASS
UITC_SM07 | Delete button | An trash bin icon should be present under the unnamed column on the right |  |  | PASS
UITC_SM08 | Back to Suppliers button | Button Label: Back to Home Button color: Blue Should be able to hear: Alt + B Back to Suppliers Page |  |  | PASS
3.5 | Manage Supplier - Functionality
FTC_SM01 | Enter data in the search box (any) | Entered data should be the only one present in the table for viewing |  |  | PASS
FTC_SM02 | Click View button | Page should be redirected to the chosen data / Supplier |  |  | PASS
FTC_SM03 | Click Edit button | Page should be redirected to the edit form of chosen data / Supplier |  |  | PASS
FTC_SM04 | Click Delete button and Cancel | A pop-up confirmation will appear: "Are you sure you want to delete this item?" Ok and Cancel button |  |  | PASS
FTC_SM05 | Click Back to Suppliers button or press Alt + H | Page should be redirected to List of Suppliers page |  |  | PASS
3.5.1 | Manage Supplier: View button - User Interface
UITC_SMV01 | Chosen Supplier Name | Chosen Supplier Name label should be present and Chosen Name should be heard |  |  | PASS
UITC_SMV02 | Update button | Button label: Update Button color: Blue Should be able to hear: Alt + U Update |  |  | PASS
UITC_SMV03 | Delete button | Button label: Delete Button color: Red Should be able to hear: Delete |  |  | PASS
UITC_SMV04 | Left columns | Left column labels should be present: ID Supplier Name Contact Number Contact Person House Number Street City Zip Code Country Email |  |  | PASS
UITC_SMV05 | Right columns | Data from Chosen Supplier Name should be present and correspond to the left column labels |  |  | PASS
UITC_SMV06 | Back to Manage Suppliers button | Button label: Back to Manage Suppliers Button color: Blue Should be able to hear: Back to Manage Suppliers Page Alt + B |  |  | PASS
3.5.2 | Manage Supplier: View button - Functionality
FTC_SMV01 | Click Update Button | Page should redirect to Update Supplier: Chosen Supplier Name |  |  | PASS
FTC_SMV02 | Click Delete Button and Cancel | A pop-up confirmation will appear: "Are you sure you want to delete this item?" Ok and Cancel button |  |  | PASS
FTC_SMV03 | Click Back to Manage Suppliers button or Press Alt + B | Page should be redirected to Manage Suppliers page |  |  | PASS
3.5.3 | Manage Supplier: Update button - User Interface
UITC_SME01 | Update Supplier: Chosen Supplier Name Label | Update Supplier Label: Chosen Supplier Name should be present |  |  | PASS
UITC_SME02 | Supplier Name textbox field | Textbox field labeled Supplier name and its data should be present Should be able to hear: Supplier Name Edit: Supplier name data |  |  | PASS
UITC_SME03 | Contact Number textbox field | Textbox field labeled Contact Number and its data should be present Should be able to hear: Contact number Edit: Contact number data |  |  | PASS
UITC_SME04 | Contact Person textbox field | Should be able to hear: Contact Person Edit: Contact Person data |  |  | PASS
UITC_SME05 | Address label | Address label should be present and "Address" should be heard |  |  | PASS
UITC_SME06 | House Number textbox field | Textbox field labeled House Number and its data should be present Should be able to hear: House Number Edit: House Number data |  |  | PASS
UITC_SME07 | Street textbox field | Textbox field labeled Street and its data should be present Should be able to hear: Street Edit: Street data |  |  | PASS
UITC_SME08 | City textbox field | Textbox field labeled City and its data should be present Should be able to hear: City Edit: City data |  |  | PASS
UITC_SME09 | Zip Code textbox field | Textbox field labeled Zip Code and its data should be present Should be able to hear: Zip Code Edit: Zip Code data |  |  | PASS
UITC_SME10 | Country dropdown list | Dropdown box labeled Country and its data should be present Should be able to hear: Country Combo box collapse: Country data |  |  | PASS
UITC_SME11 | Email textbox field | Textbox field labeled Email and its data should be present Should be able to hear: Email Edit: Email data |  |  | PASS
UITC_SME17 | Create Button | Button label: Create Button color: Green Should be able to hear: Create |  |  | PASS
UITC_SME18 | Back to Suppliers button | Button label: Back to Suppliers Button color: Blue Should be able to hear: Back to Suppliers Page Alt + B |  |  | PASS
3.5.4 | Manage Supplier: Update button - Functionality
FTC_SME01 | Edit any of the textbox and dropdown fields | User should be able to edit the following: Supplier Name Contact Number Contact Person House Number Street City Zip Code Country Email |  |  | PASS |  | Please note the remarks in the sections 3.3 and 3.3.1
FTC_SME02 | Click Update Button | Page Should be redirected to Mange Suppliers - View page and changes should be saved |  |  | PASS
FTC_SME03 | Textbox fields: Leave blank | Validation message of the following should appear: Supplier Name Contact Number Contact Person House Number Street City Email - cannot be blank |  |  | PASS
FTC_SME04 | Click Update Button | Changes should not be saved |  |  | PASS
FTC_SME05 | Click Back to Manage Suppliers button or Press Alt + B | Page should be redirected to Manage Suppliers page |  |  | PASS
PASS
FAIL
NOT RUN
BLOCKED

## Sheet2
PASS
FAIL
NOT RUN
BLOCKED
PERCENTAGE | PASS | FAIL | NOT RUN | BLOCKED
4 | 4 | 0 | 0 | 0
4.1 | 3 | 0 | 0 | 0
4.2 | 13 | 0 | 0 | 0
4.3 | 11 | 0 | 0 | 0
4.4 | 7 | 0 | 0 | 0
4.5 | 5 | 0 | 0 | 0
4.5.1 | 6 | 0 | 0 | 0
4.5.2 | 3 | 0 | 0 | 0
4.5.3 | 13 | 0 | 0 | 0
4.5.4 | 5 | 0 | 0 | 0
TOTAL | 70 | 0 | 0 | 0

## Sheet3
PASS
FAIL
NOT RUN
BLOCKED